## Slide 1
CLOUDERA EXIT
Off Cloudera, on Acceldata
In-place distribution swap · Same data, same apps · Modernize on our terms
A 6-month contract-driven program
Enterprise Data
Program Lead
Executive Briefing — Alternative Approach

## Slide 2
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Why now — and why this is a deadline, not a project
6
months to a hard stop
Cloudera contract expires. No extension available. No bridge license.
155 EDL applications
Across 9 lines of business
~66,000 tables · ~40,000 jobs
All on-prem HDFS storage
99% Sensitive / Confidential / Internal
Governance is day-one, sovereignty matters
Tableau & Power BI on top
Highest-visibility blast radius
Cloudera is the problem, not the architecture. Swap the distribution. Modernize on our terms.
Enterprise Data | Confidential
2 / 25

## Slide 3
CLOUDERA EXIT | ACCELDATA-LED APPROACH
The estate at a glance — what we're actually migrating
Line of Business
Apps
Datasets
Empty
Functions
62
26.3K
9.5K
AI Group
41
8.8K
0.9K
Personal Banking
21
11.1K
5.3K
Insurance
3
19.1K
6.3K
Capital Markets (QTS)
14
0.9K
—
Commercial Banking
9
0.4K
—
Wealth Management
3
0.4K
0.2K
Tech Infra
2
0.4K
—
Total
155
67K
22.2K
DATA CLASSIFICATION
RBC Internal
40.86%
Confidential
32.93%
Sensitive
25.95%
Restricted
0.25%
Public
0.01%
99%
of data has classifications that argue for on-prem
Sovereignty as a feature. On-prem isn't a constraint we're accepting — it's a property we're keeping.
Enterprise Data | Confidential
3 / 25

## Slide 4
CLOUDERA EXIT | ACCELDATA-LED APPROACH
The strategic frame — Cloudera is the problem, not on-prem
We are buying off Cloudera. Not buying a new architecture.
Swap Cloudera's distribution for Acceldata ODP. Same data, same apps, same SQL. Modernize deliberately in a planned Year-2 program.
1
Hit the deadline
In-place upgrades complete in 8-hour maintenance windows. Per-cluster, wave-by-wave. The contract goes away on time, with rollback paths intact.
2
Minimum disruption
Same HDFS storage. Same Hive tables. Same SQL dialect. Same BI connectivity. Apps revalidate against new binaries — no rewrites, no consumer repoints.
3
Modernize deliberately
Architectural modernization (object storage, Iceberg, Trino, Snowflake/Databricks) is a separately-funded Year-2 program with its own charter. Not a stowaway in a contract exit.
The frame matters: exec questions will probe "why not modernize while we're at it?" — this slide is the answer.
Enterprise Data | Confidential
4 / 25

## Slide 5
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Four paths off Cloudera — what we evaluated
PATH A
All-cloud
Databricks everywhere
PATH B
Mostly on-prem
Starburst + Databricks
✓ RECOMMENDED
PATH C
In-place swap
Acceldata ODP
PATH D
Snowflake-led
Snowflake + Databricks
6-month feasibility
Tight
Tight
Achievable
Tight
Per-app rework
Heavy
Heavy
Light
Heavy
BI consumer impact
Repoint
Repoint
None
Repoint
Migration risk
High
Medium
Low
High
Data sovereignty
Cloud
On-prem
On-prem
Cloud
Cost (run-rate)
Higher
Lower
Lowest
Higher
Modernization debt
Low
Low
Deferred
Low
Path C exits Cloudera fastest with minimum disruption. Deferred modernization is a deliberate choice, not an oversight.
Enterprise Data | Confidential
5 / 25

## Slide 6
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Path A — All-cloud: Databricks everywhere
PATH A
Lift the entire estate to Azure Databricks
HOW IT WORKS
ADLS Gen2 + Delta Lake for everything
Unity Catalog as governance plane
All 155 apps → Databricks Workflows + SQL Warehouse
Tableau / Power BI repoint to DBX SQL
ML / streaming native to platform
HDFS → ADLS Gen2 data movement (PB scale)
TRADE-OFFS
+
Platform already in production
+
One stack, one skill set
+
Modern ML/AI tooling out of the box
−
PB-scale HDFS → ADLS movement is critical path
−
Cloud egress / compute costs at full scale
−
Sovereignty: 99% sensitive data moves to cloud
−
Vendor concentration on Databricks
VERDICT: Feasible but tight, with sovereignty trade-off. Single-platform concentration is a real concern.
Enterprise Data | Confidential
6 / 25

## Slide 7
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Path B — Mostly on-prem: Starburst + Databricks
PATH B
Decouple compute from storage. Starburst for SQL. Databricks for ML/AI/streaming.
HOW IT WORKS
HDFS → on-prem object storage (MinIO/Ozone/ECS)
Starburst Trino: ~100 apps SQL/BI on-prem
Databricks: ~55 apps ML/AI/Spark/streaming
Hive tables stay; Iceberg in Phase 2
Ranger on-prem + Unity Catalog in cloud
Two engines, one governance posture
TRADE-OFFS
+
Modernizes architecture in one program
+
Data stays home — sovereignty intact
+
Lower run-rate (no cloud egress at SQL scale)
+
Iceberg-ready from day one
−
Heavy per-app rework (Hive SQL → Trino dialect)
−
BI consumer repoint to Starburst
−
Storage modernization on critical path
−
Two engines = two operating models
−
Higher near-term execution risk
VERDICT: Strong modernization story, but heavy per-app rework + storage modernization in a 6-month window is materially riskier than Path C.
Enterprise Data | Confidential
7 / 25

## Slide 8
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Path C — Acceldata ODP, in-place swap (recommended)
PATH C · ✓ RECOMMENDED
Swap CDP for Acceldata ODP. Same data, same apps, same SQL.
HOW IT WORKS
Acceldata ODP — Apache-aligned, vendor-supported
In-place upgrades, 8-hour maintenance windows
Per-cluster cutover, wave-by-wave
HDFS, Hive tables, Spark, Ranger all stay
Apps revalidate; no rewrites, no consumer repoints
Acceldata + RBC SI co-delivery
TRADE-OFFS
+
Lowest per-app rework — no SQL dialect changes
+
BI consumers untouched (no repoint)
+
Existing Cloudera skills transfer 1:1
+
Rollback path per cluster (<4 hours)
+
Lowest run-rate cost
+
Frees Year-2 for deliberate modernization
−
Defers architectural modernization to Year 2
−
Acceldata is a smaller vendor than Cloudera
−
Stays on HDFS / Hive tables (legacy formats)
VERDICT: Fastest path off Cloudera. Minimum disruption. Modernization deferred deliberately to a Year-2 program. Recommended.
Enterprise Data | Confidential
8 / 25

## Slide 9
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Path D — Snowflake-led migration
PATH D
Snowflake for SQL & warehousing, Databricks for ML & streaming
HOW IT WORKS
Snowflake (Azure deployment) for SQL/BI/warehousing
~100 apps SQL → Snowflake
Databricks for ML/AI/streaming (~55 apps)
ADLS Gen2 as shared storage layer (Iceberg)
Snowflake governance + Unity Catalog
Highest data velocity to cloud
TRADE-OFFS
+
Best-in-class SQL/BI performance
+
Mature governance and audit
+
Strong Tableau/Power BI ecosystem fit
−
Greenfield platform — no existing footprint
−
Two new vendor relationships in 6 months
−
PB-scale data movement to cloud
−
Compute cost model (credits) needs governance
−
Sovereignty: data leaves on-prem
VERDICT: Strong technical fit but greenfield build + cloud move in 6 months is materially riskier than Path B.
Enterprise Data | Confidential
9 / 25

## Slide 10
CLOUDERA EXIT | ACCELDATA-LED APPROACH
B vs C — the real strategic choice
Two credible paths. One question.
Are we buying off the contract, or buying off the contract AND the architecture?
PATH B
Buy off contract AND architecture
Near-term disruption
High — per-app rework, BI repoint, storage modernization
Year-2 modernization
Already done; runway free for AI/agent enablement
Risk to deadline
Real — heavy lift in tight window
What we buy
Modern architecture in 6 months
PATH C · ✓ RECOMMENDED
Buy off contract. Modernize Year 2.
Near-term disruption
Low — same SQL, same tables, same connectors
Year-2 modernization
Funded, chartered, scoped — starts ~Month 18
Risk to deadline
Lowest of the four paths
What we buy
A clean exit and a deliberate modernization runway
Why Path C: Contract-exit programs that try to modernize miss deadlines. We hit the deadline, then modernize on its own schedule.
Enterprise Data | Confidential
10 / 25

## Slide 11
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Enterprise Data | Confidential
11 / 25
Acceldata vs Pure Apache OSS — the alternative on the table
Both run the same Apache code. The difference is who carries the operational load.
ACCELDATA ODP
PURE APACHE (self-built)
Software cost
Subscription (vendor)
Zero — Apache 2.0 licensed
Integration testing
Done by Acceldata across the stack
We own — 3–5 platform engineers
CVE response
Patched distribution, vendor SLA
We scan, patch, rebuild ourselves
Migration runbooks
Provided (in-place / sidecar / forklift)
We write them
Support
24×7 enterprise SLA
Apache mailing lists, no SLA
Audit defensibility
Strong — vendor-supported platform
Weaker — self-supported
Time to first cluster
Days (public mirror)
Weeks (build pipeline + test matrix)
Exit cost
Low — runtime is open source on GitHub
N/A — already pure
Verdict: Pure Apache is a credible exit option, not a free lunch. Real cost is 3–5 dedicated platform engineers. The decision is buy support or build a team.

## Slide 12
CLOUDERA EXIT | ACCELDATA-LED APPROACH
What gets swapped — and what stays exactly where it is
SWAPPED — the actual change
Cloudera CDP binaries
→ Acceldata ODP binaries
Cloudera Manager
→ Acceldata Ambari + Pulse (optional)
Cloudera support contract
→ Acceldata support contract
Component versions
Re-validated against ODP-pinned versions
Vendor relationship
Cloudera account team → Acceldata team
Operational tooling
Re-trained on Pulse, runbooks, SLAs
STAYS — the reason this works in 6 months
HDFS storage
Same data, same paths, no movement
Hive Metastore + tables
Same schemas, same partitions
Hive / Impala SQL
No dialect translation
PySpark / Scala apps
Same code, revalidated against ODP Spark
Tableau / Power BI
Same connectors, no repoint
Ranger / Kerberos / SSO
Policies port directly
Distribution swap, not architectural change. Apps need revalidation, not rewrites. That's why this fits 6 months.
Enterprise Data | Confidential
12 / 25

## Slide 13
CLOUDERA EXIT | ACCELDATA-LED APPROACH
In-place upgrade — how a single cluster goes
Per cluster, single 8-hour maintenance window. Rollback ready in under 4 hours. Wave-based across all clusters over 26 weeks.
T-1 wk
1
Pre-stage
ODP binaries staged, validation suite prepped, rollback plan signed off.
T+0 h
2
Stop services
Drain workloads, snapshot HMS, capture Ranger policies, freeze writes.
T+1 h
3
Install ODP
Acceldata binaries installed parallel to CDP; configs migrated via runbook.
T+3 h
4
Bring services up
HMS, Ranger, HDFS NameNode, YARN, Spark, Hive — all on ODP.
T+5 h
5
Smoke test
Validation suite: sample queries, key apps, BI connectivity check.
T+7 h
6
Go / no-go
Named app owners sign off OR rollback initiated (<4 hours).
T+8 h
7
Window closes
Cluster live on ODP, hypercare team on standby for 72 hours.
Same data. Same Hive Metastore. Same tables. Same SQL. Only the binaries change.
Enterprise Data | Confidential
13 / 25

## Slide 14
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Enterprise Data | Confidential
14 / 25
Acceldata offers three upgrade paths — pick by infra, not by name
In-place, sidecar, forklift. Same destination. Different risk profile, different prerequisites.
1. IN-PLACE
Upgrade the existing cluster
What
Same iron, same data. CDP binaries swapped for ODP binaries in place.
Window
8-hour maintenance window per cluster
Rollback
Under 4 hours
Best for
Already on ODP, or aggressive CDP exit on same hardware
Risk
Concentrated — one window, full cluster
2. SIDECAR
Run both, migrate gradually
What
New ODP cluster runs parallel to CDP. Workloads cut over wave by wave.
Window
Per-wave cutovers, no platform-wide window
Rollback
Instant — workload stays on CDP if validation fails
Best for
Same site, mixed workload risk, MR-heavy estates
Risk
Distributed — longer parallel period, more validation effort
3. FORKLIFT
New infra, phased move
What
Stand up ODP on new hardware or cloud. Decommission CDP after migration.
Window
No CDP impact during migration
Rollback
Flexible — CDP stays available until cutover
Best for
Hardware refresh or cloud migration coinciding with the exit
Risk
Procurement + dual-running cost stretches the timeline
What changes by path: infrastructure, parallelism, and rollback shape. What doesn't change: the destination platform, application code, data layer, governance model.

## Slide 15
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Enterprise Data | Confidential
15 / 25
Sidecar upgrade — parallel cluster, wave-based migration
OUR RECOMMENDED PATH
HOW IT WORKS
Stand up a new ODP cluster alongside CDP, same site or different.
Replicate HDFS / Hive metastore / Ranger policies to ODP.
Migrate workloads in waves: Spark first (lowest risk), then Hive, then MR last.
Each wave gets parallel validation: identical job runs on both clusters, output diffed.
Cutover when wave passes validation. CDP stays running until last wave is migrated.
Decommission CDP after final wave + hypercare period.
TRADE-OFFS
PROS
+
Lowest risk: each wave validates independently; failed wave doesn't impact others.
+
MR off the critical path: legacy MR jobs can stay on CDP until retired.
+
Instant rollback: if validation fails, workload stays on CDP. No 4-hour reversal.
+
Allows ODP performance baselining against CDP under real load.
CONS
−
Requires parallel hardware capacity (or temporary cloud burst).
−
Longer parallel run = double operational cost during transition.
−
Data sync between clusters needs design effort.
Verdict: right fit for our 55/35/10 mix. Keeps MR off the critical path and gives us validation safety. The cost is parallel hardware and longer dual-run.

## Slide 16
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Enterprise Data | Confidential
16 / 25
Forklift upgrade — new infrastructure, phased move
ALTERNATIVE PATH
HOW IT WORKS
Provision entirely new infrastructure — new hardware on-prem, or cloud (AWS/Azure/GCP).
Build ODP cluster from scratch on the new infrastructure.
Migrate data and workloads in phases over weeks or months.
CDP estate remains untouched until decommission decision.
Decommission CDP once all workloads are validated on ODP.
Typically paired with a strategic infra decision (cloud move, hardware refresh).
TRADE-OFFS
PROS
+
Zero impact on CDP estate during build phase.
+
Forces hardware refresh and modernization in one motion.
+
Cleanest separation: easy to walk away if ODP underperforms.
+
Natural fit if cloud strategy is already approved.
CONS
−
Procurement cycle can consume a full month before any work starts.
−
Dual-running infra cost is the highest of the three paths.
−
Couples platform + infra decisions — 3-month timeline becomes unrealistic.
Verdict: right answer only if we're funded for hardware refresh or cloud move at the same time. For a pure Cloudera exit, sidecar is the cheaper, faster, lower-risk version of the same idea.

## Slide 17
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Enterprise Data | Confidential
17 / 25
Our recommendation — sidecar with in-place fallback
Three paths exist. For our estate, mix, and timeline — sidecar is the right default. In-place is the fallback for clusters where parallel hardware isn't an option.
RECOMMENDED: SIDECAR (PRIMARY) + IN-PLACE (FALLBACK PER CLUSTER)
01
Workload mix demands it
55% Spark / 35% Hive / 10% MR. MR is the schedule risk — sidecar keeps it on CDP until retired. In-place would force a same-window MR migration.
02
Validation safety
Spark 3.3 → 3.3.3 and Hive 3.1.3 → 3.1.x should be clean, but JDK 17 uplift is the real unknown. Sidecar runs the diff in parallel before commit.
03
Procurement leverage
Sidecar's longer parallel run keeps CDP available — buys negotiating time with Acceldata. No forced cutover, no contract panic.
FALL BACK TO IN-PLACE PER CLUSTER WHEN:
• No parallel hardware capacity for that cluster • Workload is uniform and well-validated • Contract deadline pressure on that specific cluster
Forklift only if a separate hardware-refresh or cloud-migration program is already funded.

## Slide 18
CLOUDERA EXIT | ACCELDATA-LED APPROACH
The SWAT team — one small core, clear ownership
Program Lead
Named
Single accountable owner end-to-end. Wave plan, RAID, exec cadence.
Product Lead
Named
Stakeholder management across 9 LOBs. App owner sign-offs, wave content.
SRE Lead
Named
Reliability across maintenance windows, smoke-test gate, hypercare ownership.
Project Governance
Named
Decision flow, change control, audit trail, RAID hygiene.
Acceldata Lead
TBD
ODP rollout, vendor liaison, runbook execution, Pulse onboarding.
SI Partner Lead
Named
Validation engineering, wave delivery, app team coordination, hypercare.
One open seat. Acceldata lead must be named in Week 1 — vendor procurement and validation suite are the critical path.
Enterprise Data | Confidential
18 / 25

## Slide 19
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Phased plan — five phases, wave-based cluster cutovers
1
DISCOVER
W1–4
Profile 155 apps
Inventory 66K tables
Cluster wave plan locked
Validation suite scoped
2
STAND UP
W2–10
Acceldata contract signed
SI partner engaged
ODP staged on test cluster
Validation suite built
3
VALIDATE
W4–22
Wave-by-wave validation
App owner sign-offs
Smoke tests per cluster
Rollback drills
4
CUTOVER
W10–24
8-hour maintenance windows
Per-cluster cutover
<4 hour rollback ready
Hypercare per wave
5
DECOMMISSION
W24–26
Cloudera shutdown
Contract obligations met
Year-2 charter approved
Lessons learned
Validate, validate, cut over. Every cluster cutover is a planned weekend window. Apps revalidate against ODP before signing off.
Enterprise Data | Confidential
19 / 25

## Slide 20
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Workstreams — who owns what
ODP Platform Build
Acceldata + Internal
ODP staging, runbook prep, Pulse onboarding, support model setup.
Validation Engineering
SI partner + Internal
Test suites per app class. Smoke tests, regression, performance baselines.
App Owner Coordination
Product Lead + Internal
Per-app sign-off cadence, wave assignment, hypercare contact tree.
Acceldata Vendor Mgmt
Program Lead
Contract, due diligence, SLA enforcement, runbook escalation.
SI Partnership
Program Lead + SI
Accenture / Deloitte / IBM. Wave delivery muscle, validation execution.
Hypercare
SRE Lead + Internal
72-hour post-cutover support per cluster. War room model on each wave.
Enterprise Data | Confidential
20 / 25

## Slide 21
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Timeline — 26 weeks, critical path is procurement + validation
W0
W4
W8
W12
W16
W20
W24
Discover
Acceldata procurement
SI partner engagement
Validation suite build
ODP staging (test cluster)
Wave validations
Cluster cutovers
Hypercare
Decommission
M1
M2
M3
M4
M1 Discover · M2 First cluster cut over · M3 70% cut over · M4 Final cutover
Red = critical path. Acceldata contract must close by Week 6. Validation suite must be ready by Week 10. Slippage here = missed deadline.
Enterprise Data | Confidential
21 / 25

## Slide 22
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Operating cadence — rhythm, not status meetings
Cadence
Forum
Purpose
DAILY
Wave standups
Blocker clearing per active wave. 15 minutes. Issues escalate to SWAT same day.
WEEKLY
Program standup
Cross-stream dependencies, RAID review, wave health. All workstreams.
WEEKLY
Infra sync
Network, compute, storage. Critical-path workstream gets its own room.
BI-WEEKLY
Steering (EVP + VP)
Decisions only — not status. If steering becomes a status forum, decisions queue and we slip.
PER WAVE
Go / no-go review
Named sign-offs from app owners and BI consumers before cutover. No sign-off, no swing.
MONTHLY
Sponsor readout
Milestones, RAID, decisions taken, decisions needed. Status flows here.
Steering exists to unblock. Decision rights: scope or schedule changes need steering sign-off; operational decisions stay with the SWAT.
Enterprise Data | Confidential
22 / 25

## Slide 23
CLOUDERA EXIT | ACCELDATA-LED APPROACH
Top risks & mitigations
Risk
Severity
Impact
Mitigation
Acceldata vendor risk
HIGH
Smaller vendor than Cloudera. Financial, strategic, or M&A event could leave us exposed mid-program.
Full due diligence (financial, security, OSFI). Source-code escrow. Multi-year support contract with exit clauses.
App revalidation gaps
HIGH
Subtle behavior differences between CDP and ODP binaries surface only under production load.
Comprehensive validation suite per app class. Smoke-test gate at T+5h. Hypercare model for 72h post-cutover.
Maintenance window blowouts
MED
Single cluster cutover exceeds 8-hour window; rollback window (<4h) gets eaten.
Per-cluster rollback drills before cutover. Named decision-maker for go/rollback at T+7h.
Custom UDFs / SerDes
MED
Java extensions written against specific Cloudera APIs may not work on ODP binaries.
Inventory in Discovery (W1–4). Vendor-supported port path for known cases; reject others to Year 2.
Modernization debt accumulation
MED
If Year-2 charter doesn't get funded, we sit on HDFS / Hive tables indefinitely.
Year-2 charter approved as a precondition for the program. Funded line item in FY26 plan.
Team retention / motivation
MED
Team may lose interest if they see this as "keep doing Hadoop forever."
Year-2 charter named publicly; team members rotate into modernization roles after cutover.
Enterprise Data | Confidential
23 / 25

## Slide 24
CLOUDERA EXIT | ACCELDATA-LED APPROACH
What we need from you — in the next two weeks
1
Program authority
Endorse Path C as the enterprise approach. Cover for scope freeze. Confirm the recommendation publicly to set the tone with LOBs and the team.
2
Acceldata due diligence
Approve immediate vendor diligence: financial review, security review, OSFI submission, source-code escrow terms. Cannot start without this.
3
Partner engagement
Approve Acceldata contract + RBC SI (Accenture / Deloitte / IBM) co-delivery model. Release named internal SMEs from competing initiatives.
4
Year-2 modernization charter
Approve and FUND a Year-2 modernization charter (~Month 18 start). Without this commitment the deferral is not credible to the team or to audit.
Enterprise Data | Confidential
24 / 25

## Slide 25
WHAT SUCCESS LOOKS LIKE AT MONTH 6
Off Cloudera. Same data, same apps. Modernization runway intact.
0
Cloudera workloads remaining
Contract obligations met on time
155
Apps live on Acceldata ODP
Same SQL, same BI, same code
66k
Tables — exactly where they were
HDFS unchanged, HMS intact, governance ported
Year-2 modernization charter kicks off Month 18 — Iceberg, object storage, Trino on its own schedule
Lowest risk. Lowest disruption. Same deadline. Modernization happens deliberately, not under contract pressure.
Confidential | Enterprise Data | 25 / 25